## Schedule
Phase	Task / Milestone	Description	Start date	Planned finish date	Actual finish date	Dependency	Comment
Phase I – FWP	2	Finalize R&D TOF design	Feb-19	Jun-19			Need Design Eng
	4	Simulate reducing signal	Feb-19	Jun-19			Ongoing
	6	Iterate Simulation and Eng. Design of R&D TOFs	Apr-19	Jul-19			Ongoing
	8	Order 2 initial R&D TOFs	May-19	Aug-19
	10	Order 6 R&D TOFs	Sep-19	Dec-19
	12	Initial Digitizer arrival	Jan-19	May-19
	14	Other three digitizers	May-19	Sept. 2019
	16	Iterate Chamber Eng. Design	Jun-19	Aug-19			Need Design Eng
	18	Order initial R&D MCP (2)	May-19	Aug-19
	20	Order full set of R&D MCPs (6)	Jul-19	Nov. 2019
	M1	Prototype Chamber Final Design		Aug-19		16	PEC for XIP
	22	Order Prototype mu metal chamber	Sep-19	Jan-20		M1	Lead time = 3-6 months
	24	Assemble Prototype	Dec-19	Feb. 2020		M1, 22	need 4-6 weeks
	M2	(Adjust) Final Design TMO version Chamber Design and make FDR		Feb. 2020			XIP FDR

Phase II - XIP	28	Order Parts	Jan-20
	30	Assemble	Jul-20
	32	Test	Aug-20
	34	Offline commissioning	Oct-20
	M3	RFI
	36	Install MRCOFFE in TMO	Dec-20
	M4	TTO		Apr-21
	M5	Project closeout		Sept-21